## Defect Tracking Log
DEFECT TRACKING LOG
Project Name
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 3.1.2026. | Slaven Nedić, Amel Fehrić, Nihad Mandžo | 1. Open the browser 2. Go to www.amazon.com 3. Search for a product e.g. "table" 4. Make sure the lowest price is selected (price slider dragged to the beginning) 5. Select the "Price: Low to High" sorting option 6. The products listed have prices lower than the minimum displayed on the price slider to the left Video: https://edufit-my.sharepoint.com/:v:/g/personal/slaven_nedic_edu_fit_ba/IQDm9dhMreIWRJrq530oswOJAWfdLN1mpltuc3Dj2JFMgfk?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=OQWCDC | [11 empty] | New
2 | 3.1.2026. | Slaven Nedić, Amel Fehrić, Nihad Mandžo | 1. Open the browser 2. Go to www.amazon.com 3. Search for a product e.g. "table" 4. Make sure the lowest and highest prices are selected (price slider dragged to the beginning and to the end) 5. Select the "Price: Low to High" sorting option 6. The price slider min and max values change when sorted by featured vs any other sorting option, none of them should affect the min and max price values, only sort the already existing items Video: visible in the video from the first defect | [11 empty] | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 5.1.2026 | Amel Fehrić, Nihad Mandžo, Slaven Nedić | 1.Open the Brave browser 2.Go to amazon.com 3.Start writing or copy dummy text into search bar 4.Paste multiple times dummy text or write around 30 000 characters Results:After 30 000 characters web app amazon starts lagging after few more characters web app freezes(unable to refresh page) Proof:https://www.youtube.com/watch?v=hIUG0OvpiwA&list=PLh1HTAxS0yiyGsifICeUpuxY6GWgNG279&index=4 | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 5.1.2026 | Amel Fehrić, Nihad Mandžo, Slaven Nedić | 1.Open the Brave browser 2.Go to amazon.com 3.Search for "bookshelf bookshelf bookshelf bookshelf" 4.First page shows 1-48, 30,000 results and 7 pages 5.Going through pages results vary 6.Go to page 17 then 18 Results: After page 17 results drastically change from 252-272 over 60,000 results to 273-288 of over 1,000 results and pages change from 400 to 68 Proof: https://www.youtube.com/watch?v=c7E8GoxyzwA&list=PLh1HTAxS0yiyGsifICeUpuxY6GWgNG279&index=5 | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 5.1.2026 | Amel Fehrić, Nihad Mandžo, Slaven Nedić | 1.Open the Brave browser 2.Go to amazon.com 3.Search for "iphone" in search bar 4.Go to filters and choose model year 2023 5.Find model year in filter menu Results: Model Year 2024 will show after selecting 2023. Proof: https://www.youtube.com/watch?v=rMusAZPzeh0&list=PLh1HTAxS0yiyGsifICeUpuxY6GWgNG279&index=8 | [6 empty] | New | [6 empty] | Executing/Controlling | Design
6 | 5.1.2026 | Amel Fehrić, Nihad Mandžo, Slaven Nedić | 1.Open the Brave browser 2.Go to amazon.com 3.Login or register then login 4.Select Country:USA 5.Rufus will show then select rufus AI beta 6.Window will show on side 7.Type "best seller men's shoes that are made in 2025 size 12 color black brands nike or addidas" Results: Rufus will give some shoes that are not made in 2025. Proof: https://www.youtube.com/watch?v=3NJn_tKUN0A&list=PLh1HTAxS0yiyGsifICeUpuxY6GWgNG279&index=9 | [6 empty] | New | [6 empty] | Closing | Development
7 | 5.1.2026 | Amel Fehrić, Nihad Mandžo, Slaven Nedić | 1.Open the Mozilla Firefox browser 2.Go to amazon.com 3.Sign in to amazon 4.Add items to cart(54) 5.Add another item Result: You can't add more than 54 items in cart after trying to add 55 item it deletes previous item and make counter go down. Proof: https://www.youtube.com/watch?v=KXwuTk4cDQA&list=PLh1HTAxS0yiyGsifICeUpuxY6GWgNG279&index=1 | [6 empty] | New | [7 empty] | Testing
8 | 5.1.2026 | Amel Fehrić, Nihad Mandžo, Slaven Nedić | 1.Open the Brave browser 2.Go to amazon.com 3.Sign in to amazon 4.Add item to cart(order amount not limited by user) for example Wilson GST Leather Game Football 5.Order 10 same products 6.Type in the Qty field 99999 Result: Trying to order 10 of the same products unlocks field Qty you can write huge number in it like 99999. After adding number product will remove itself from cart Proof: https://www.youtube.com/watch?v=qcAIuiT-IAY&list=PLh1HTAxS0yiyGsifICeUpuxY6GWgNG279&index=3 | [6 empty] | New | [7 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).